## Gantt Chart
Blood Donation Finder — Project Gantt Chart
Phase | Task | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Notes
INITIATION
Initiation | Group formation | [13 empty] | Team roles & responsibilities assigned
Initiation | Project finalization | [13 empty] | Scope, proposal & tech stack confirmed
PLANNING & SETUP
Planning & Setup | Requirements & wireframes | [13 empty] | Includes ER diagram & UI mockups
Planning & Setup | DB schema design | [13 empty] | MySQL schema for users, requests, chat
Planning & Setup | Project & env setup | [13 empty] | Node/Express/MySQL boilerplate
CORE DEVELOPMENT
Core Development | Auth & user registration | [13 empty] | JWT auth, donor & org flows
Core Development | Blood request system | [13 empty] | CRUD for blood requests
Core Development | Donor matching logic | [13 empty] | City/district-based filtering
Core Development | Request status tracking | [13 empty] | Open / Fulfilled / Expired states
SECONDARY FEATURES
Secondary Features | Email notifications | [13 empty] | Nodemailer + Gmail SMTP
Secondary Features | In-app chat (Socket.io) | [13 empty] | Real-time donor-requester chat
Secondary Features | Donation history log | [13 empty] | Per-user donation records
TESTING & DELIVERY
Testing & Delivery | Integration testing | [13 empty] | End-to-end flow testing
Testing & Delivery | Bug fixes & polish | [13 empty] | UI polish, edge cases
Testing & Delivery | Deployment & demo prep | [13 empty] | Deploy + presentation prep
GENERAL
Documentaion | Documentaion | [13 empty] | Continuous throogh out the project
LEGEND
Initiation
Planning & Setup
Core Development
Secondary Features
Testing & Delivery
General